## Sayfa1
proje adimlari | sure dk
splash screen arayuz tasarimi | 60
splash screen kodlamasi | 60
login arayuz tasarim | 60
login sayfa kodlamasi | 60
MainForm arayuz tasarimi | 60
MainFormKodlamasi | 60
studentForm arayuzTasarimi | 60
studentFormKodlamasi | 60
sql student tablo olusturma | 40
BOOKSForm arayuz Tasarimi | 60
BOOKSFormKodlanmasi | 40
sql book tablo olusturma | 45
LibrariansForm arayuz Tasarimi | 60
LibrariansFormKodlsmasi | 40
sql librarian tablo olusturma | 45
Return BooksForm arayuz Tasarim | 60
:Return BooksFormKodlamasi | 60
sql return tablo olusturma | 60
Issue BooksForm arayuz Tasarim | 70
Issue BooksFormKodlamasi | 50
sql issue tablo olusturma | 45
connect to the database and insert librarians in the data base | 120
display the added data in datagridview for librarians form | 120
codding edit-delet button for librarians form | 90
connect to the database and insert Student in the data base for Student form | 120
display the added data in datagridview for Student form | 120
coding the edit -delet button for Student form | 90
connect to the database and insert book in the data base for book form | 120
display the added data in datagridview for issue books form | 120
codding edit-delet button for issue books form | 90
connect to the database and insert issue in the data base for books form | 120
display the added data in datagridview for book form | 120
codding delet button for book form | 90
connect to the database and insert Student in the data base for return book form | 120
display the added data in datagridview for return book form | 120
codding return issue book button and delete button for return book form | 90
issue book formunda açılan kutulari student ve book tablosundaki verilerle dolduruma | 90
issuebook ve return book bilgileri gunceleme test etme ve dogrulama | 120
AboutUs arayuz tasarimi | 60
AboutUs form kodlamasi | 60
DashBord form arayuz tasarimi | 60
DashBord form arayuz kodlamasi | 60
login form da login button database ile baglama | 90
proje dosyalarının apdate ve test edilmesi | 180
tips form aryuz tasarim | 60
tips form kodlama | 60